## Slide 1: 2017 Summer Deliverable Calendar
Term Week | Due Date | Item(s) | Submit To
1 | 6/8 | 1) Handbook Forms, 2) Info Sheet, 3) Personality Assessments, 4) Entrance Personal Growth Assessment, 5) DEVELOPedia Participant Page, 6) Orientation Completed | 1) CLs LFT to Jennifer Tindell, 2) CLs LFT to Georgina, 3) Tiffani, 4) Google Form, 5) DEVELOPedia
3 | 6/22 | Project Summary RD | PC Team Gmail
4 | 6/29 | 1) Tech Paper RD, 2) Code Meeting this week (if applicable) | 1) PC Team Gmail, 2) Geoinformatics
5 | 7/4 | Offices Closed for Independence Day | 
5 | 7/6 | 1) Poster RD, 2) Presentation RD, 3) Video Outline, 4) Software Release Forms (if applicable) | 1-2) PC Gmail, 3) Comm Gmail, 4) Jordan
6 | 7/13 | Project Summary FD, Study Area Shapefiles, Website/Booklet Image | PC Gmail
7 | 7/20 | HQ Poster FD, HQ Presentation FD | PC Gmail
8 | 7/25 | 1) Project Video & Transcript, 2) Draft Code (if applicable) | 1) Comm Google Drive, 2) Geo Email
9 | 8/3 | 1) Exit Personal Growth Assessment, 2) Poster FD, 3) Presentation FD, 4) DEVELOPedia Project Page | 1) Google Form, 2-3) PC Gmail, 4) DEVELOPedia
10 | 8/10 | Tech Paper FD, Technical Image | PC Gmail
10 | 8/11 | 1) Exit Survey, 2) Optional Deliverables 3) Code with README (if applicable) | 1) Google Form, 2) PC Gmail 3) Geo Email

## Slide 2: 2017 Summer Deliverable Calendar
Orientation, Surveys & Forms, Applications | Meet & Greets, Practices, Presentations, Interviews | Project Summary | Study Area Shapefiles | Imagery | Tech Paper | Poster | Presentation | Video: Outline, Video & Transcript | Optional Deliverables
Wk 1
Wk 2
Wk 3
Wk 4
Wk 5
Wk 6
Wk 7
Wk 8
Wk 9
Wk 10
National Orientation, Entrance PGA, Info Sheet, Handbook Forms
Fall Application Deadline, Fellow/CL Application Deadline
Fellow / CL Interviews
Fellow / CL Interviews, Project Video Team Check ins
Fellow / CL Interviews
Fellow / CL Selections
NPO Meet & Greets, Geo Team Tag Ups,
Tech Paper Webinar
HQ Practice Presentations
HQ Summer Showcase
Geo Team Tag Ups
Rough Draft
Rough Draft
Rough Draft
Rough Draft
Video Outline
Partner Handoffs, Node Close outs
Website / Booklet
Technical
Final Draft for Booklet & Website
Final Draft
Archive Final Draft
Archive Final Draft
Final Video & Transcript
HQ Final Draft
HQ Final Draft
Software Release Forms
Shapefiles
DEVELOPedia Project Page
Archive Draft
Code, Tutorials, Brochures
Draft Code to Geoinformatics
Code Shepherd Introduction & Planning
Video Team Check-Ins