## Slide 1
2019 Summer
NATIONAL
ORIENTATION
MODULE 10. Project Lead Orientation
Notes: Your project Website Image should be placed behind the hexagon grid. An example image has been placed in this position for your reference. Delete the example image, insert your image, right click your image and select the “Send to Back” option. Position and adjust the size of your image so that it lines up with the provided margin rulers.

## Slide 2
Project Lead Duties
Ensure the team is on schedule and meets deadlines
Empower team members to take on different pieces of the project and ensures that all tasks are delegated, but Project Leads work on the project too!
Serve as the main POC to the Fellow Teams and NPO
Submit deliverables
Respond to edits, feedback, and questions from the PC Team
Report progress and challenges to the Center Lead regularly
Lead communications with partners and coordinates telecons, meetings, and project hand-offs
Understand your teams strengths and weaknesses
Foster a positive team dynamic and work environment
By The Way
Project Leads are selected based off of a number of factors and experiences – they do not always have the most technical skills of the team. That’s ok!
Know your strengths – you are capable!

## Slide 3
Leading Means…
Possess a clear vision of the future and be compelled by it.
Encourage people to share ideas, needs, perspectives, dreams, and desires.
Stand for, demonstrate, and portray what you believe.
Empower people with the authority to use their own skills and knowledge.
Evaluate the people who work with them and the performance of the team.
Inspire and motivate others with passion and example.
“When you include and acknowledge those in your corner, you propel yourself, your teammates, and your supporters to greater heights.”
- Simon Sinek

## Slide 4
Leadership Styles
 | Directive | Authoritative | Affiliative | Participative | Pacesetting | Coaching
Characteristics | Motivates by discipline, closely controls participants | Firm but fair, motivates by persuasion and candid feedback on performance | “People first”, avoids conflict and emphasizes personal relationships | “Everyone has input”, encourages decision making and rewards team effort | “Do it myself”, expects participants to follow their example of excellence | Encourages participants to develop strengths, improve performance, and seize opportunity
Good when… | There is a crisis or deviations are risky | Clear direction and standards are needed and leader is credible | Used with other styles, tasks are routine | Participants are communicative, experienced, and credible | Participants are highly motivated and competent | Skills need to be developed and participants are motivated to improve
Bad when… | Participants are too underskilled or too overskilled and they rebel | Participants need coaching and the leader is not credible | Performance is inadequate and during crisis situations | Employees need to be managed, lack of competency | Workload requires assistance and coaching is required | Leader lacks expertise and when discrepancy in skill is too large

## Slide 5
Creating Your Leadership Style
Situational Context
Personality
Leadership Style
Response

## Slide 6
Project Duties & Responsibilities
Your primary responsibility is to ensure the project is completed on time to a high quality.
By The Way
Project Leads are the main point of contact for project communication with multiple parties during (and after) the term.
Key Things to Remember | Some Tips & Tricks
Time management | Make a schedule & keep files & tasks organized.
Leading a team | Incorporate feedback from team members and Center Leads. Delegate to team members.
Managing project challenges | Be flexible & build in time to troubleshoot issues with your project methodology.
Communication | Maintain open and consistent communication with node leadership, NPO, science advisors & all partners.
End products & partner hand-off | Begin planning for hand-off & software release early in the term.

## Slide 7
Deliverable Management
Deliverables communicate your project purpose, methodology, and results to a variety of audiences
You are tasked with ensuring that high-quality deliverables are created and submitted
Key Things to Remember | Some Tips & Tricks
Name files according to proper file nomenclature | YearTerm_NODE_DeliverableName_RD/FD_Version#
Follow deliverable template formatting | Reference DEVELOPedia for the deliverable templates & checklists.
Review deliverables before submission | Quality of writing, style, accuracy, etc. Incorporate feedback from Node leadership Address edits & comments from the PC team
Submit deliverables on time | Be mindful of deliverable deadlines.

## Slide 8
Additional Responsibilities
Software Release
Publication
Submit to NPO.
Communicate with Partners.
Create well documented and transferrable code.
Follow-up paperwork & code handoff with Partners.
Notify NPO.
Research specific journals’ publication requirements & style guide.
Continue working with NPO after the term during the publication process.

## Slide 9
Team Management
It is important to know your team’s strengths and interests in the project
Consider activities and exercises for team members to get to know each other.
  Hold ice breakers at the beginning of the term.
  Continue having team activities throughout the term (lunches & outings!).
Understand team dynamics and delegate tasks accordingly.
  Know team members’ personalities (NASA 4D and MBTI) and how they interact with others.
  Identify the best ways to handle personnel issues when they arise.
Find out the individual goals & expectations of your team members.
  Strike a balance between team members’ learning and productivity.
  Learn team member objectives for their time with DEVELOP and beyond.
  Incorporate feedback from team members (mid-term reviews).

## Slide 10
Conflict Resolution
It is important that different people & personalities can come together as a team.
Some Topics to Discuss with Your Team | How This Can Be Applied
Does your NASA 4D color match what you thought you would get? Why or why not? | Use this discussion to let your team members know that personality typing is a guide, not a verdict.
What are the strengths and weaknesses of each team member’s personality type? | Come prepared with some challenge scenarios related to the project and ask each team member how they might handle them (i.e. workload causing stress, collaborating across different work schedules, etc.).
If conflict arises how would you try to mitigate it? | Again, come prepared with scenarios: a team member is making inappropriate comments, showing up to work late, etc. ALL participants should let the Center Lead know of any conflict that arises.
By The Way
Communicate with your Center Lead about ANY personnel issues, no matter how minor, they need to be aware!

## Slide 11
Partner Interaction
DEVELOP projects are created to meet partners’ needs & build capacity.
Always be honest with your partners. Do not be afraid to give them updates (good or bad) or ask them for assistance.
Key Things to Remember | Some Tips & Tricks
Maintain consistency | Establish a regular schedule & follow through.
Keep node leadership informed | Include node leadership and your team on all partner communication (email & telecon).
Represent your team & DEVELOP at all times | Always maintain professional email and telecon etiquette.
Increase available data/resources | Ask for any data/resources that partners may have that could be useful. And ask early!

## Slide 12
Managing Partner Expectations
Remember: Partners are the ones who will be using the project results.
Maintain communication throughout the term.
Do not over commit on what you can accomplish or provide in one term.
Always follow through on promises.
Ensure end products meet partner needs.

## Slide 13
Hand-Off
Hand-offs are important to transition results and methods to end users
Best Practices
  Talk with your project partners early on in the term about scheduling a hand-off.
  Identify what type of hand-off will be most beneficial (feasible) for partners & the team.
  Coordinate with all partners to ensure all interested parties can attend (keep in mind there may be differences in time zones).
  Include your final draft deliverables in any hand-off package that you share.
  Explain the Software Release process & timeline to partners in advance.
  Follow up with your end-users to receive feedback or answer any questions (especially on multi-term projects).

## Slide 14
Communicating Across DEVELOP
At your node…. | With science advisors...
Talk with node leadership regularly. | Invite your advisors to team & partner meetings.
Include Center Leads & team on all partner interactions (emails, calls, etc.). | Communicate regularly with advisors as their schedules allow.
Ask your node leadership for help if you need additional resources. | Ask advisors for help in all aspects of the project (including deliverable edits, methodology, & end products).
Inform your node leadership if you plan on undergoing the publication process. | Always exercise professional email & telecon etiquette when communicating with advisors.
Ask Fellows for help on tasks related to their Element responsibilities. | Include your advisors in email communication with project partners.

## Slide 15
Communicating w/NPO
DEVELOP NPO | Ask them about…
Project Coordination | Deliverables & publishing
Geoinformatics | Coding, technical troubleshooting, & data
Impact Analysis | Program, project, & partner metrics
Communications | Graphic design, social media, & creating the project video
IT | DEVELOPedia, software release, licensing, & general computer issues

## Slide 16
Email Signature & Résumé/LinkedIn
Being the lead of your team is great opportunity and you should highlight it!
Colloquially leads are sometimes referred to as “Team Lead”, but formally it’s “Project Lead”
  This is more clear externally as you are leading a science project and leading a “team” is vague.
Email Signature:
Name
Project Short Title Project Lead
Science Systems and Applications, Inc.
Node|NASA DEVELOP National Program
Office: XXX-XXX-XXXX
  Colors and fonts, etc. are up to you, but the above information and basic format should be used.
Example:
Loretta Landsat
Ohio Water Resources Project Lead
Science Systems and Applications, Inc.
Virginia – Langley |NASA DEVELOP National Program
Office: 757-555-5555

## Slide 17
When In Doubt
Google it.
Look on DEVELOPedia.
Look at past projects.
Ask your team.
Ask your Center Lead.
Ask your Science Advisor.
Ask a Fellow.
Ask NPO.
They are here to support you and ensure your success!

## Slide 18
THANK YOU!
“Being positive in negative situations is not naive. It’s leadership”
– Ralph Marston
Notes: Your project Website Image should be placed behind the hexagon grid. An example image has been placed in this position for your reference. Delete the example image, insert your image, right click your image and select the “Send to Back” option. Position and adjust the size of your image so that it lines up with the provided margin rulers.