## Slide 1: 2018 Spring Deliverable Calendar
Term Week | Due Date | Item(s) | Submit To
1 | 1/25 | 1) Handbook Forms, 2) Info Sheet, 3) Personality Assessments, 4) Entrance Personal Growth Assessment, 5) DEVELOPedia Participant Page, 6) Orientation Completed | 1) CLs LFT to Karen, 2) CLs LFT to Georgina, 3) Amanda, 4) Google Form, 5) DEVELOPedia
3 | 2/8 | Project Summary RD | PC Gmail
4 | 2/15 | 1) Tech Paper RD, 2) Code Meeting this week (if applicable) | 1) PC Team Gmail, 2) Geoinformatics
5 | 2/19 | Offices Closed for President’s Day | 
5 | 2/22 | 1) Video Outline, 2) Software Release Definition Document (if applicable) | 1) Comm Gmail, 2) Jordan
6 | 3/1 | 1) Poster RD, 2) Presentation RD | 1-2) PC Gmail
7 | 3/8 | 1) Project Summary FD, 2) Study Area Shapefiles, 3) Website Image, 4) Software Release Master Document (if applicable) | 1-2) PC Gmail, 3) Comm Gmail, 4) Jordan
8 | 3/15 | 1) Project Video & Transcript, 2) Software Release Draft Code (if applicable) | 1) Comm Google Drive, 2) Geo Gmail
9 | 3/22 | 1) Poster FD, 2) Presentation FD, 3) DEVELOPedia Project Page | 1-2) PC Gmail, 3) DEVELOPedia
10 | 3/26 | Exit Personal Growth Assessment | Google Form
10 | 3/29 | 1) Tech Paper FD, 2) Project Feedback Form, 3) Technical Image | 1-2) PC Gmail, 3) Comm Gmail
10 | 3/30 | 1) Exit Survey, 2) Optional Deliverables 3) Software Release Code with README (if applicable) | 1) Google Form, 2) PC Gmail 3) Geo Gmail

## Slide 2: 2018 Spring Deliverable Calendar
Orientation, Surveys & Forms, Applications | Meet & Greets, Practices, Presentations, Interviews | Project Summary | Study Area Shapefiles | Imagery | Tech Paper | Poster | Presentation | Video: Outline, Video & Transcript | Code & Optional Deliverables
Wk 1
Wk 2
Wk 3
Wk 4
Wk 5
Wk 6
Wk 7
Wk 8
Wk 9
Wk 10
National Orientation, Entrance PGA, Info Sheet, Handbook Forms, Personality
Summer Application Deadline
Exit PGA
NPO Meet & Greets
Close Out Practices, Summer Interviews
Rough Draft
Rough Draft
Rough Draft
Rough Draft
Video Outline
Partner Handoffs, Node Close outs
Website
Technical
Final Draft
Final Draft
Final Draft
Final Draft
Final Video & Transcript
Software Release Definition Document
Shapefiles
DEVELOPedia Project Page
Software Release Final Code, Tutorials, Brochures
Software Release Draft Code
Video Team Check-Ins
Lit Review
NPO Meet & Greets
Lit Review
Lit Review
Software Release Code Meeting
Feedback Form, Exit Survey
Software Release Master Document
Tech Paper Webinar
Summer Interviews